## Tasks
Dino Hunt — implementation task tracker
Greenfield build · Fusion + Nevermore · place 96665470525866 · plan: docs/06-project-plan.md
Edit only the Status and Notes columns. Everything else is derived from the plan.
ID | Phase | Area | Task | Acceptance criteria | Depends on | Est (d) | Pri | Status | FR ref | Notes
DH-001 | 0 | Toolchain | Install and pin Rokit toolchain | rokit.toml pins rojo, wally, selene, stylua; `rokit install` succeeds |  | 0.25 | M | Cut |  | Void — no Rojo/Wally. Decided 2026-09-28.
DH-002 | 0 | Toolchain | Pin Fusion and Nevermore in wally.toml | Exact versions pinned, not ranges. Fusion major recorded in docs (0.3 changed the API). | DH-001 | 0.5 | M | Cut |  | Void — no Wally. Fusion installed from its GitHub .rbxm instead; Nevermore dropped.
DH-003 | 0 | Toolchain | Write default.project.json | Maps src/shared, src/server, src/client, src/assets per plan section 3 | DH-001 | 0.25 | M | Cut |  | Void — no Rojo.
DH-004 | 0 | Toolchain | Selene and StyLua config | Both run clean on an empty project | DH-001 | 0.25 | M | Not started |  | Can still run manually against exported source.
DH-005 | 0 | Structure | Create src skeleton | shared/Config, shared/Net, shared/Types, shared/Util, server/Services, client/Controllers, client/UI | DH-003 | 0.25 | M | Done |  | Built in-place: ReplicatedStorage.Shared{Config,Net,Types,Util}, Server.Services, Client{Controllers,UI}.
DH-006 | 0 | Structure | ServiceBag bootstrap | init.server.luau builds the bag and starts services; init.client.luau mirrors it | DH-005 | 0.5 | M | Done |  | ServiceBag + Bootstrap live. Server log: '0 service(s)', no errors.
DH-007 | 0 | Toolchain | Prove the Rojo round trip | Edit a file, Rojo syncs, change visible in Dino Hunt place | DH-006 | 0.25 | M | Cut |  | Void — no Rojo. MCP set_script_source is the authoring path.
DH-008 | 0 | UI | Reference Fusion component | One trivial HUD element renders in-game from a file edit. Sets the pattern for every later component. | DH-007 | 0.5 | M | Done |  | Client.Bootstrap renders the HUD; Computed followed Value 0->1. Fusion 0.3 confirmed.
DH-009 | 0 | Process | Commit the skeleton | Pushed to master; wally.lock committed | DH-008 | 0.25 | M | Not started
DH-010 | 1 | World | Blockout: reactor core and defense ring | Central structure with a visibly read defense ring on the floor | DH-009 | 0.5 | M | Not started | FR-10
DH-011 | 1 | World | Blockout: approach lanes and spawn markers | 2-3 lanes that read clearly from the reactor; spawn points marked | DH-010 | 0.5 | M | Not started
DH-012 | 1 | World | Blockout: sector volumes and gates | Four bounded areas behind gate volumes | DH-010 | 0.5 | M | Not started | FR-30
DH-013 | 1 | World | Export blockout to .rbxmx | Committed under src/assets; replaceable without touching code | DH-012 | 0.25 | M | Not started
DH-014 | 1 | Config | Species table and derivation formulas | One lp weight per species; baseHP/damage/rewards all derived. Comment the constants. | DH-009 | 0.5 | M | Not started | FR-60
DH-015 | 1 | Creature | Grey-box rig: swarmer | Part-built, distinct silhouette, flat colour, walk cycle only | DH-009 | 0.5 | M | Not started | FR-60
DH-016 | 1 | Creature | CreatureService: spawn and pooling | Pooled instances; no per-spawn instantiation spikes | DH-014 | 0.75 | M | Not started | NFR-P5
DH-017 | 1 | Creature | Concurrency cap from day one | min(perPlayer x live, MAX_ACTIVE); one server-wide cap | DH-016 | 0.25 | M | Not started | NFR-P2
DH-018 | 1 | Creature | Pathing to the reactor | Creature walks a lane and reaches the defense ring | DH-016 | 0.75 | M | Not started
DH-019 | 1 | Combat | CombatService: hitscan rifle | Server-validated: fire rate, ammo, origin sanity | DH-006 | 1 | M | Not started | NFR-S1
DH-020 | 1 | Combat | Damage, death and the one-shot invariant | Wave-1 creature dies to exactly one starter shot | DH-019 | 0.5 | M | Not started | FR-61
DH-021 | 2 | Wave | WaveService: 20 finite wave definitions | Wave counter reaches 20; no wave 21 | DH-020 | 1 | M | Not started | FR-01
DH-022 | 2 | Wave | Wave composition table in Config | Per-wave species and counts; sums verified | DH-021 | 0.5 | M | Not started
DH-023 | 2 | Wave | Batched spawning from a reservoir | Concurrency cap never exceeded mid-wave | DH-022 | 0.5 | M | Not started | NFR-P2
DH-024 | 2 | Wave | Intermission (15s) | Timer visible; buy actions available | DH-021 | 0.5 | M | Not started | FR-05
DH-025 | 2 | Creature | Grey-box rig: flanker | Medium, lean silhouette | DH-015 | 0.4 | M | Not started | FR-60
DH-026 | 2 | Creature | Grey-box rig: armoured | Wide, tall front plate | DH-015 | 0.4 | M | Not started | FR-60
DH-027 | 2 | Creature | Grey-box rig: ranged | Medium with a marked head; telegraphed spit | DH-015 | 0.6 | M | Not started | FR-60
DH-028 | 2 | Combat | Directional armour | Shots blocked within a cone of facing; land from the flank | DH-026 | 0.75 | M | Not started
DH-029 | 2 | Wave | Victory at wave 20 | Victory screen; rewards granted once | DH-021 | 0.4 | M | Not started | FR-02
DH-030 | 2 | Wave | Defeat state stub | Placeholder until the reactor exists | DH-021 | 0.25 | M | Not started | FR-03
DH-031 | 3 | Objective | Reactor instance and server-owned HP | HP replicates; not client-writable | DH-010 | 0.5 | M | Not started | FR-10
DH-032 | 3 | Objective | Reactor damage intake and ring targeting | Creatures reaching the ring attack it; HP falls | DH-031 | 0.75 | M | Not started | FR-11
DH-033 | 3 | Objective | Repair interaction | Hold-interact; costs Credits; rate from Config | DH-032 | 0.5 | M | Not started | FR-12
DH-034 | 3 | Objective | Defeat on reactor at 0 HP | Defeat screen; checkpoint rewards retained | DH-032 | 0.4 | M | Not started | FR-03
DH-035 | 3 | Economy | Amber drops, server-owned | Amber never enters a backpack | DH-031 | 0.5 | M | Not started | FR-13
DH-036 | 3 | Economy | Amber magnet flight and gauge | 0.5-1.2s curve; value added exactly once; VFX culled on low-end | DH-035 | 0.75 | M | Not started | FR-14
DH-037 | 3 | Economy | Reactor levels 1-5 | Level-up fires once per threshold | DH-036 | 0.5 | M | Not started | FR-15
DH-038 | 3 | Economy | Party-scaled Amber thresholds | Solo and 6-player reach L2 at a comparable wave. Fixes a GDD defect. | DH-037 | 0.5 | M | Not started | FR-16
DH-039 | 3 | UI | Fusion HUD: reactor HP | Reads clearly at a glance; low-HP state distinct | DH-031 | 0.4 | M | Not started
DH-040 | 3 | UI | Fusion HUD: Amber gauge | Shows current level and progress to next | DH-037 | 0.5 | M | Not started
DH-041 | 3 | UI | Fusion HUD: wave counter and enemies remaining | Top-centre per the GDD HUD spec | DH-021 | 0.4 | M | Not started
DH-042 | 4 | Boss | BossService: phase state machine | Phases advance on HP thresholds; recovers from a lost target | DH-021 | 1 | M | Not started | FR-20
DH-043 | 4 | Boss | Telegraph system and ground indicators | Readable at the lowest graphics setting | DH-042 | 0.75 | M | Not started | FR-22 NFR-U5
DH-044 | 4 | Boss | Invulnerability cap | No boss invulnerable more than 8 consecutive seconds; instrumented | DH-042 | 0.25 | M | Not started | FR-21
DH-045 | 4 | Boss | Fusion boss health bar | Phase markers visible | DH-042 | 0.4 | M | Not started
DH-046 | 4 | Boss | Boss 1: Alpha Raptor Matriarch | Summons, hunter mark, wall-leap, flank window after a missed pounce | DH-043 | 1.25 | M | Not started | FR-25
DH-047 | 4 | Boss | Checkpoint reward and phase respawn | Exactly one reward; downed players respawn once at a transition | DH-045 | 0.5 | M | Not started | FR-23 FR-24
DH-048 | 4 | Exploration | ExplorationService: wave pause | No spawns, no reactor damage during exploration | DH-045 | 0.5 | M | Not started | FR-32
DH-049 | 4 | Exploration | 150s timer with 30s and 10s warnings | Warnings fire once each | DH-047 | 0.4 | M | Not started | FR-33
DH-050 | 4 | Exploration | Safe recall at zero | Distant players recalled, not killed. No fall damage. | DH-048 | 0.5 | M | Not started | FR-34
DH-051 | 4 | Exploration | Sector 1 gating on boss AND Amber level | Neither condition alone opens it | DH-038 | 0.5 | M | Not started | FR-30
DH-052 | 4 | Exploration | Late gauge fill case | If the gauge fills mid-wave, the sector opens then. Defines what the GDD leaves open. | DH-050 | 0.5 | M | Not started | FR-31
DH-053 | 5 | Survivor | SurvivorService: escort NPC and waypoints | Authored waypoints, not dynamic pathfinding | DH-050 | 1 | M | Not started | FR-40
DH-054 | 5 | Survivor | Stuck recovery | Relocates to the last safe waypoint after 8s | DH-052 | 0.4 | M | Not started | FR-41
DH-055 | 5 | Survivor | Safe room arrival and team credit | Credit shared team-wide; survivor visibly present | DH-052 | 0.4 | M | Not started | FR-40
DH-056 | 5 | Hatchery | Nest and guardian | Kill OR distract both yield the egg | DH-050 | 0.75 | M | Not started | FR-42
DH-057 | 5 | Hatchery | Egg carry state | Occupies an objective slot, slows sprint, icon above carrier | DH-055 | 0.5 | M | Not started | FR-43
DH-058 | 5 | Hatchery | Hatchery deposit secures the egg | Survives a forced run loss | DH-056 | 0.5 | M | Not started | FR-44
DH-059 | 5 | Hatchery | Incubation on server timestamps | Survives reconnect. Timestamp-based, never tick-based. | DH-057 | 0.75 | M | Not started | FR-45 NFR-D4
DH-060 | 5 | Hatchery | Idempotent pet grant | Exactly one pet. Duplicate grant IDs rejected. HIGHEST data-integrity risk. | DH-058 | 0.75 | M | Not started | FR-46 NFR-D3
DH-061 | 5 | Collection | Dino Codex (minimal) | Seen / defeated / egg / hatched per species; persists | DH-059 | 0.75 | S | Not started | FR-47
DH-062 | 5 | Data | DataService profile keys | DinoCodex, EggInventory, PetInventory, SurvivorLog; schema versioned | DH-059 | 0.5 | M | Not started | NFR-D5
DH-063 | 6 | Player | Three classes with passives | Ranger, Engineer, Medic. Duplicates allowed. | DH-021 | 0.75 | M | Not started | FR-50
DH-064 | 6 | Player | Class abilities on 60s cooldown | Scan Pulse, Shock Fence, Healing Mist | DH-062 | 0.75 | M | Not started | FR-50
DH-065 | 6 | Player | Downed state (25s) | Not instant death | DH-020 | 0.4 | M | Not started | FR-51
DH-066 | 6 | Player | Revive (3s, interrupted by damage) | Verified in multiplayer | DH-064 | 0.4 | M | Not started | FR-52
DH-067 | 6 | Player | Next-wave respawn and credit penalty | Solo case explicitly defined. Fixes a GDD contradiction. | DH-064 | 0.4 | M | Not started | FR-53
DH-068 | 6 | Player | Run perks: milestone 3-choice draft | Six perks; stacks respected | DH-021 | 0.6 | S | Not started | FR-06
DH-069 | 6 | Hardening | Performance pass | 50+ FPS on reference mobile at wave 20; memory flat across a run | DH-060 | 0.75 | M | Not started | NFR-P1 NFR-P4
DH-070 | 6 | Hardening | Mobile device test | Touch reaches every action; UI never blocks controls | DH-068 | 0.5 | M | Not started | NFR-C2 NFR-C4
DH-071 | 6 | Hardening | Exploit pass | Forged hits, forged rewards, duplicate egg grants all rejected | DH-060 | 0.75 | M | Not started | NFR-S1 NFR-S5
DH-072 | 6 | Hardening | Bug fix and stabilisation buffer | Reserved. Do not plan work into it. | DH-070 | 1 | M | Not started
DH-073 | 0 | Process | Export the script tree to the repo | export_rbxm of the code tree committed to git — the only version control the code has | DH-008 | 0.25 | M | Not started | Added 2026-09-28: no Rojo means no automatic git coverage.
DH-074 | 0 | Process | Write Maid/Signal/ServiceBag unit checks | Each exercised in a playtest: cleanup runs, signal fires, two-phase init order holds | DH-006 | 0.5 | S | Not started | Added 2026-09-28: hand-written replacements for Nevermore need proving.
|  |  | 74 tasks |  | TOTAL | 39.9

## Phases
Phase rollup
Every figure here is a formula over the Tasks sheet. Nothing to edit.
Phase | Name | Goal | Tasks | Done | Est (d) | Done (d) | % complete | Exit criteria
0 | Toolchain | Nothing else can start until this is done | 11 | 3 | 3.75 | 1.25 | 33.33% | A trivial Fusion HUD element renders in-game from a file edit
1 | Blockout and creature stub | Prove one creature, one gun, one lane | 11 | 0 | 6 | 0 | 0% | A creature walks a lane and dies to one rifle shot
2 | The wave loop | Twenty finite waves with four creature roles | 10 | 0 | 5.3 | 0 | 0% | A full 20-wave run completes
3 | The spine | Something to defend; the run can be won or lost | 11 | 0 | 5.7 | 0 | 0% | A run can be won and lost; the reactor is the objective
4 | Boss and exploration | The loop the game is actually about | 11 | 0 | 6.55 | 0 | 0% | Wave 4 boss to sector opens to exploration to safe return
5 | The collection loop | The reason players come back | 10 | 0 | 6.3 | 0 | 0% | An egg survives a disconnect and hatches into exactly one pet
6 | Players and hardening | Make it hold up | 10 | 0 | 6.3 | 0 | 0% | MVP slice exit criteria met
| TOTAL |  | 74 | 3 | 39.9 | 1.25 | 3.133%
Estimates assume one developer working with Claude Code. Phase 6's buffer is reserved — do not plan work into it.

## Legend
How to use this tracker
Editing | Change only the Status and Notes columns on the Tasks sheet. Everything else mirrors docs/06-project-plan.md; if the plan changes, the tracker is regenerated from it.
Status values
Not started | Default. No work begun.
In progress | Actively being worked.
Blocked | Cannot proceed. Say why in Notes — and if it is a real decision, raise it in docs/03-open-decisions.md.
Done | Acceptance criteria met in a Studio play test, verified solo and with 2+ players, no new console errors.
Cut | Deliberately dropped. Say why in Notes.
Priority
M | Must have for the MVP slice.
S | Should have. Cut first if a phase overruns.
C | Could have.
Columns
Depends on | The task ID that must be Done first. Blank means it can start once its phase does.
Est (d) | Developer-days. Fractions are deliberate — most tasks are hours, not days.
FR ref | The functional or non-functional requirement in docs/archive/05-sdlc-plan.md. Those 64 requirements survived the greenfield restart unchanged.
Definition of Done | Acceptance criteria met · verified solo AND multiplayer · no new console errors across a full wave · server-authoritative · numbers live in src/shared/Config with a derivation comment · committed and pushed.
Invariants | Never break these: wave-1 creature dies to exactly one starter shot · every creature is slower than the player · nothing one-shots a full-health player · one server-wide concurrency cap · the client never reports a hit.